## Summary
Ag. Nikolaos Home — Project Balance Sheet
Financial ground truth. Currency: EUR. Last updated 2026-10-05. Sources: project folder, Drive payments sheet, WhatsApp 'Evia HOME', Gmail, bank confirmations.
FUNDING & POSITION
Total deposited into NBG | 320000 | 6 transfers Sep-2025 to May-2026 (bank statement)
Property acquisition (2025) | 171709 | Contract price €145,000 + legal/notary/tax
Current NBG balance | 49805 | Reported 2026-10-05 (see Reconciliation > Rolling Bridge for the residual check)
RENOVATION
Renovation paid to date | 108161.47 | All methods, de-duplicated
Committed (approved, unpaid) | 15945 | Electrician, metalworker, insurance, etc.
Acquisition + Renovation paid | 279870.47 | Total cash deployed into the project to date
RECONCILIATION CHECK
NBG reconciliation difference | 0 | Account ties to the official statement (zero)
⚑ Open items needing your confirmation are on the 'Flags & Dedup' tab.

## Renovation Ledger
Renovation Ledger — Ag. Nikolaos Home
Every renovation expense (Jan–Jun 2026), de-duplicated. The €380 demolition hammer drill (18-Jun) is a SEPARATE payment, paid by Vicky's card, to be deducted from the Antonis contract.
Report Date | Category | Description | Vendor / Payee | Amount (€) | Method | From NBG? | Status | Payment Date
2026-01-17 | Waste/Bins | Recycle/waste bins (8) | Kairis | 992 | cash | Yes | Paid | 2026-01-17
2026-01-17 | Labour | Team leader/manager (11 days) | Meli | 880 | cash | Yes | Paid | 2026-01-17
2026-01-17 | Labour | Workers (18 worker-days) | Workers | 900 | cash | Yes | Paid | 2026-01-17
2026-01-17 | Electrical | Electricity materials | Supplier | 250 | cash | Yes | Paid | 2026-01-17
2026-01-17 | Equipment | Tool damage replacement | - | 250 | cash | Yes | Paid | 2026-01-17
2026-01-24 | Waste/Bins | Recycle/waste bins (2) | Kairis | 248 | cash | Yes | Paid | 2026-01-24
2026-01-24 | Materials | Cement - large storage base | Amanatidis | 431.48 | NBG card | Yes | Paid | 2026-01-24
2026-01-24 | Labour | Workers (16 worker-days) | Workers | 800 | cash | Yes | Paid | 2026-01-24
2026-01-24 | Labour | Team leader (7 days) | Meli | 560 | cash | Yes | Paid | 2026-01-24
2026-01-24 | Equipment | Tool spare parts/materials | Poutichidis | 120 | cash | Yes | Paid | 2026-01-24
2026-01-24 | Materials | Steel - large storage base | Kairis | 350 | cash | Yes | Paid | 2026-01-24
2026-02-02 | Materials | Steel reinforcements | Kairis | 220 | cash | Yes | Paid | 2026-02-02
2026-02-02 | Materials | Cement - large storage slab | Amanatidis | 800.07 | NBG card | Yes | Paid | 2026-02-02
2026-02-02 | Labour | Team leader (5 days) | Meli | 400 | cash | Yes | Paid | 2026-02-02
2026-02-02 | Labour | Workers (7 worker-days) | Workers | 350 | cash | Yes | Paid | 2026-02-02
2026-02-02 | Waste/Bins | Recycle/waste bins (2) | Kairis | 248 | cash | Yes | Paid | 2026-02-02
2026-02-02 | Materials | Steel - large storage base | Kairis | 350 | cash | Yes | Paid | 2026-02-02
2026-02-07 | Other | Soula - inconvenience & water | Soula | 50 | cash | Yes | Paid | 2026-02-07
2026-02-07 | Labour | Workers (9 worker-days) | Workers | 450 | cash | Yes | Paid | 2026-02-07
2026-02-07 | Labour | Team leader (5 days) | Meli | 400 | cash | Yes | Paid | 2026-02-07
2026-02-07 | Waste/Bins | Recycle/waste bins (1) | Kairis | 124 | cash | Yes | Paid | 2026-02-07
2026-02-07 | Fuel | Fuel - concrete mixer (storage slab) | Gas station | 30 | cash | Yes | Paid | 2026-02-07
2026-03-16 | Labour | Workers (12 wd) - storage/road/trees/elec | Workers | 600 | cash | Yes | Paid | 2026-03-16
2026-03-16 | Labour | Team leader (3 days) | Meli | 240 | cash | Yes | Paid | 2026-03-16
2026-03-16 | Legal/Admin | Municipality road-barrier removal | Municipality | 350 | cash | Yes | Paid | 2026-03-16
2026-03-16 | Electrical | Electrician - bury backyard line + materials | Electrician | 600 | cash | Yes | Paid | 2026-03-16
2026-03-16 | Site Works | Excavator + 8 gravel trucks (160m road) | Alexiou | 3700 | cash | Yes | Paid | 2026-03-16
2026-03-16 | Materials | Kairis - Ytong + glue (storage walls) | Kairis | 2216 | cash | Yes | Paid | 2026-03-16
2026-05-07 | Legal/Admin | Workers insurance Jan-Feb (60 work-days) | EFKA | 2200 | cash | Yes | Paid | 2026-05-07
2026-03-21 | Materials | Kairis - roof insul/steel/fiberboard (adv.) | Kairis | 500 | cash | Yes | Paid | 2026-03-21
2026-03-21 | Labour | Team leader (5 days) | Meli | 400 | cash | Yes | Paid | 2026-03-21
2026-03-21 | Labour | Workers (6 worker-days) | Workers | 300 | cash | Yes | Paid | 2026-03-21
2026-03-21 | Legal/Admin | Greek SIM (Kobi) | Zoe | 50 | cash | Yes | Paid | 2026-03-21
2026-03-21 | Materials | Glass bricks - storage | Supplier | 75 | cash | Yes | Paid | 2026-03-21
2026-03-21 | Landscaping | Gardener (Mar-Apr) | Gardener | 200 | cash | Yes | Paid | 2026-03-21
2026-03-28 | Materials | Kairis - internal walls 1F (bricks/steel/sand) | Kairis | 2950 | cash | Yes | Paid | 2026-03-28
2026-03-28 | Labour | Team leader (3 days) | Meli | 240 | cash | Yes | Paid | 2026-03-28
2026-03-28 | Labour | Workers (6 worker-days) | Workers | 300 | cash | Yes | Paid | 2026-03-28
2026-04-04 | Labour | Brick workers - first floor | Workers | 930 | cash | Yes | Paid | 2026-04-04
2026-04-07 | Landscaping | Gardener pipes/hoses | Gardener | 100 | cash | Yes | Paid | 2026-04-07
2026-04-07 | Roof | Kairis - large storage roof materials | Kairis | 1350 | cash | Yes | Paid | 2026-04-07
2026-04-07 | Plumbing | Plumbing pipes floor1+storage (card part) | Supplier | 1140 | NBG card | Yes | Paid | 2026-04-07
2026-04-07 | Plumbing | Plumbing pipes floor1+storage (cash part) | Supplier | 660 | cash | Yes | Paid | 2026-04-07
2026-04-09 | Plumbing | Plumber advance #1 | Plumber | 1000 | cash | Yes | Paid | 2026-04-09
2026-04-21 | Plumbing | Additional plumbing materials | Supplier | 660 | cash | Yes | Paid | 2026-04-21
2026-04-21 | Materials | Storage insulation materials | Kairis | 1600 | cash | Yes | Paid | 2026-04-21
2026-04-28 | Labour | Team leader (8 days) - storage+house | Meli | 640 | cash | Yes | Paid | 2026-04-28
2026-04-28 | Labour | Workers (13 worker-days) | Workers | 650 | cash | Yes | Paid | 2026-04-28
2026-04-30 | Plumbing | Plumber advance #2 - additional work | Plumber | 1000 | cash | Yes | Paid | 2026-04-30
2026-05-10 | Labour | Team leader (8 days) - back gate/small storage | Meli | 640 | cash | Yes | Paid | 2026-05-10
2026-05-10 | Labour | Workers (16 worker-days) | Workers | 800 | cash | Yes | Paid | 2026-05-10
2026-05-10 | Fuel | Fuel - cement mixer | Gas station | 30 | cash | Yes | Paid | 2026-05-10
2026-05-10 | Windows/Iron | Advance - ironworker (large storage door) | Blacksmith | 350 | cash | Yes | Paid | 2026-05-10
2026-05-10 | Legal/Admin | Workers social security (remaining) | EFKA | 200 | cash | Yes | Paid | 2026-05-10
2026-05-10 | Materials | Kairis - forms/iron/cement/coat/lime | Kairis | 1750 | cash | Yes | Paid | 2026-05-10
2026-05-09 | Materials | Amanatidis - extra materials | Amanatidis | 205.75 | NBG card | Yes | Paid | 2026-05-09
2026-03-23 | Materials | Amanatidis - materials | Amanatidis | 87.02 | NBG card | Yes | Paid | 2026-03-23
2026-05-16 | Windows/Iron | Old front gate repair + wheels | Blacksmith | 50 | cash | Yes | Paid | 2026-05-16
2026-05-16 | Plumbing | Plumber payment #3 | Plumber | 500 | cash | Yes | Paid | 2026-05-16
2026-05-16 | Roof | Kairis - 3F panels+small-storage roof+Ytong+coat | Kairis | 2875 | cash | Yes | Paid | 2026-05-16
2026-05-16 | Electrical | Electrician advance - Apt B conduits | Electrician | 400 | cash | Yes | Paid | 2026-05-16
2026-05-16 | Labour | Team leader (6 days) | Meli | 480 | cash | Yes | Paid | 2026-05-16
2026-05-16 | Labour | Workers (16 worker-days) | Workers | 800 | cash | Yes | Paid | 2026-05-16
2026-05-23 | Windows/Iron | Aluminium inner door+window - large storage (TECHNICAL) | TECHNICAL | 1150 | NBG card | Yes | Paid | 2026-05-23
2026-05-23 | Labour | Workers (18 wd) week May19-23 | Workers | 900 | cash | Yes | Paid | 2026-05-23
2026-05-23 | Labour | Team leader Meli (4 days) | Meli | 320 | cash | Yes | Paid | 2026-05-23
2026-05-23 | Labour | Replacement contractor (4 days) | Contractor | 400 | cash | Yes | Paid | 2026-05-23
2026-05-23 | Waste/Bins | Kairis - waste containers (3) | Kairis | 360 | cash | Yes | Paid | 2026-05-23
2026-05-23 | Materials | Kairis - upper floor materials | Kairis | 100 | cash | Yes | Paid | 2026-05-23
2026-05-26 | Materials | Kairis - partial debt settlement (of €3,335) | Kairis | 2330 | cash | Yes | Paid | 2026-05-26
2026-05-26 | Legal/Admin | Owner certificates x2 (Yael+Kobi) | Vasiliki | 200 | transfer (NBG) | Yes | Paid | 2026-05-26
2026-05-18 | Legal/Admin | Tax registration - accountant (SIANOS) | Accountant | 711 | NBG card | Yes | Paid | 2026-05-18
2026-05-06 | Legal/Admin | Land registry - temporal certification | Land registry | 100 | transfer (NBG) | Yes | Paid | 2026-05-06
2026-05-25 | Labour | Ice cream - worker treat | Meli Ice Cream | 50 | cash | Yes | Paid | 2026-05-25
2026-05-28 | Site Works | Excavator - open + close plumbing/electrical channels | Excavator | 600 | cash | Yes | Paid | 2026-05-28
2026-05-28 | Plumbing | Plumber - 3 days corner-to-corner pipe sealing | Plumber | 1000 | cash | Yes | Paid | 2026-05-28
2026-05-28 | Electrical | Electrician advance - power to Yael unit | Electrician | 1000 | cash | Yes | Paid | 2026-05-28
2026-05-28 | Plumbing | Plumber - materials & pipes (infrastructure) | Plumber | 300 | cash | Yes | Paid | 2026-05-28
2026-06-01 | Labour | Workers wages week May26-31 | Workers | 1500 | cash | Yes | Paid | 2026-06-01
2026-06-01 | Materials | 3-component epoxy coating - Yael unit floor | Supplier | 400 | cash | Yes | Paid | 2026-06-01
2026-06-06 | Labour | Workers wages week Jun2-6 | Workers+Meli | 1780 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Materials | Precast septic rings+cover+crane - Yael unit | Supplier | 650 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Waste/Bins | Kairis - waste container | Kairis | 125 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Fuel | Site fuel | Gas station | 50 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Other | Old mattress removal - front area | Removal | 50 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Materials | Kairis - 10 sacks (running tab) | Kairis | 105 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Materials | Kairis - partial payment (of €4,045) | Kairis | 2000 | cash | Yes | Paid | 2026-06-06
2026-06-06 | Plumbing | Bathroom fixtures - Yael unit | Diamantopoulos | 614 | Wise | No | Paid | 2026-06-06
2026-06-07 | Labour | Workers Jun7 Sunday (Meli+1) | Workers | 130 | cash | Yes | Paid | 2026-06-07
2026-06-13 | Plumbing | Transport - bathroom supplies from Athens | Istiaia transport | 45 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Workers Mon+Tue (4/day) | Workers | 400 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Meli Mon+Tue | Meli | 160 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Workers Wed+Thu (4+ESAT) | Workers | 500 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Meli Wed+Thu | Meli | 160 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Workers Fri+Sat (5+ESAT) | Workers | 600 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Meli Fri+Sat | Meli | 160 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Ilir - roof welding (Fri) | Ilir | 300 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Labour | Ilir - roof welding (Sat) | Ilir | 300 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Fuel | Site fuel week Jun8-13 | Gas station | 40 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Materials | Kairis materials week Jun8-13 | Kairis | 450 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Electrical | Extension cable | Supplier | 75 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Materials | Tarpaulin (rain protection) | Supplier | 75 | cash | Yes | Paid | 2026-06-13
2026-06-13 | Materials | Concrete roof anchors + resin | Supplier | 80 | cash | Yes | Paid | 2026-06-13
2026-06-15 | Materials | Kairis - partial payment (bal -> ~€400) | Kairis | 2000 | cash | Yes | Paid | 2026-06-15
2026-06-18 | Materials | Athens shopping - Yael unit fit-out (door/AC/heater/window/access.) | Athens suppliers | 972.55 | card (Vicky) | No | Paid | 2026-06-18
2026-06-24 | Equipment | Demolition hammer drill (STRIGOS) - charge to Antonis contract | STRIGOS SERVICE | 380.6 | NBG card | Yes | Paid | 2026-06-24
2026-06-19 | Tiles | Spanish tiles 'Crosscut Marfil' 60x60 25.88m² | Tsintonis | 286 | Wise | No | Paid | 2026-06-19
2026-06-22 | Labour | Workers week Jun16-21 (incl polished cement) | Workers+Meli | 2280 | cash | Yes | Paid | 2026-06-22
2026-06-22 | Materials | Kairis materials week Jun15-21 | Kairis | 1175 | cash | Yes | Paid | 2026-06-22
2026-06-22 | Furniture | Iron bed frame+bedside tables+slats - Yael | Supplier | 350 | cash | Yes | Paid | 2026-06-22
2026-06-22 | Furniture | Bedding/pillows/bedspread - Yael unit | Vicky | 155 | card (Vicky) | No | Paid | 2026-06-22
2026-06-22 | Fuel | Site fuel week Jun16-21 | Gas station | 40 | cash | Yes | Paid | 2026-06-22
2026-06-24 | Materials | Kairis debt settlement (old bal+materials) | Kairis | 1800 | cash | Yes | Paid | 2026-06-24
2026-06-24 | Materials | Beam (structural) + rendering materials | Kairis | 420 | cash | Yes | Paid | 2026-06-24
2026-06-25 | Furniture | Custom mattress - Yael unit (195x170 30cm) | Local mfr | 400 | cash | Yes | Paid | 2026-06-25
2026-06-27 | Materials | Cleaning materials - Yael unit (Jun 27) | Supplier | 150 | cash | Yes | Paid | 2026-06-27
2026-07-05 | Materials | Sand and gravel - week Jun29-Jul5 | Supplier | 150 | cash | Yes | Paid | 2026-07-10
2026-07-05 | Fuel | Fuel - concrete mixers week Jun29-Jul5 | Gas station | 40 | cash | Yes | Paid | 2026-07-10
2026-07-05 | Materials | Steel reinforcement - wall bond beams above door openings | Supplier | 400 | cash | Yes | Paid | 2026-07-10
2026-07-05 | Materials | Kairis - column reinforcement steel, cement, resin anchors | Kairis | 1800 | cash | Yes | Paid | 2026-07-10
2026-07-05 | Labour | Workers wages - week Jun29-Jul5 | Workers | 1910 | cash | Yes | Paid | 2026-07-10
2026-07-10 | Materials | Kairis - SikaGrout/reinforcement materials (partial payment toward new balance) | Kairis | 1700 | cash | Yes | Paid | 2026-07-10
2026-07-12 | Labour | Workers wages - week Jul7-12 | Workers | 2150 | cash | Yes | Paid | 2026-07-12
2026-07-19 | Labour | Workers wages Mon-Wed - week Jul13-19 | Workers | 900 | cash | Yes | Paid | 2026-07-20
2026-07-19 | Equipment | Concrete mixer - week Jul13-19 | Site | 20 | cash | Yes | Paid | 2026-07-20
2026-07-19 | Materials | Binding wire and steel-tying materials - week Jul13-19 | Supplier | 65 | cash | Yes | Paid | 2026-07-20
2026-07-23 | Materials | Kairis - cash payment toward outstanding materials debt (applied to column/beam debt + additional item) | Kairis | 3000 | cash | Yes | Paid | 2026-07-23
2026-07-27 | Labour | Workers wages + concrete mixer cost, week of Jul20-24 (small crew, few days on site) | Site crew | 680 | cash | Yes | Paid | 2026-07-27
2026-07-29 | Materials | Kairis - cash payment toward outstanding materials debt (remainder applied to next SikaGrout order) | Kairis | 3000 | cash | Yes | Paid | 2026-07-29
2026-09-25 | Materials | Kairis - cash payment toward SikaGrout order balance (Vicky Sep 29: balance now EUR4,400 after this payment) | Kairis | 2350 | cash | Yes | Paid | 2026-09-25
2026-09-25 | Other | Remainder of Sep 25 EUR3,000 NBG withdrawal - cash float, allocation TBC (nails/steel strips ~EUR45, mixer petrol; possibly water fee EUR400 / ELEC deposit) | Vicky (cash float) | 650 | cash | Yes | Paid | 2026-09-25
2026-09-29 | Materials | Kairis - EUR1,000 payment toward SikaGrout balance from Sep 29 EUR3,000 withdrawal (inferred: NBG balance Oct 5 ties to three EUR3,000 withdrawals since Jul 29) | Kairis | 1000 | cash | Yes | Paid | 2026-09-29
2026-10-03 | Labour | Workers wages - week Sep 28-Oct 3 (4/4/3/4/3/3 workers Mon-Sat) | Site crew | 1510 | cash | Yes | Paid | 2026-10-03
2026-10-03 | Fuel | Fuel - week Sep 28-Oct 3 (EUR2.20/l) | Site | 50 | cash | Yes | Paid | 2026-10-03
2026-10-03 | Materials | Construction materials - week Sep 28-Oct 3 | Supplier | 150 | cash | Yes | Paid | 2026-10-03
2026-10-03 | Materials | Kairis - EUR1,050 payment toward SikaGrout debt (EUR3,000 -> EUR1,950 remaining) | Kairis | 1050 | cash | Yes | Paid | 2026-10-03
2026-06-28 | Materials | Materials - week Jun25-28 (Yael unit completion) | Kairis | 1500 | cash | Yes | Paid | 2026-06-29
2026-06-28 | Plumbing | Plumber - Yael unit completion | Plumber | 200 | cash | Yes | Paid | 2026-06-29
2026-06-28 | Labour | Carpenter - Yael unit (bedside tables/countertop/door) | Carpenter | 250 | cash | Yes | Paid | 2026-06-29
2026-06-28 | Materials | Marble for shower - Yael unit | Supplier | 50 | cash | Yes | Paid | 2026-06-29
2026-06-28 | Fuel | Site fuel week Jun25-28 | Vicky | 40 | cash | Yes | Paid | 2026-06-29
2026-06-28 | Labour | Workers week Jun25-28 (Yael unit + site) | Workers | 2600 | cash | Yes | Paid | 2026-06-29
2026-05-23 | Electrical | Electrician - 2 apts+2 storages+outdoor | Electrician | 9500 | cash | Yes | Committed
2026-05-23 | Electrical | Electrical plans - submitted to authority | Electrician | 1000 | - | Yes | Committed
2026-05-23 | Electrical | Three-phase meter (Kobi's name) | Electrician | 750 | - | Yes | Committed
2026-05-23 | Electrical | Electrician advance - 130m piping reimb. | Electrician | 1000 | cash | Yes | Committed
2026-05-23 | Windows/Iron | Metalworker - small storage door+window | Metalworker | 550 | cash | Yes | Committed
2026-06-15 | Site Works | Excavator - road compaction (60t roller) | Excavator | 600 | cash | Yes | Committed
2026-07-20 | Legal/Admin | Worker insurance Apr-Jun - partial payment | EFKA | 1865 | cash | Yes | Paid | 2026-07-20
2026-07-21 | Legal/Admin | Worker insurance Apr-Jun - second partial payment | EFKA | 1990 | cash | Yes | Paid | 2026-07-21
2026-06-25 | Legal/Admin | Worker insurance Apr-Jun - remaining balance | EFKA | 3 | - | Yes | Committed
2026-07-19 | Materials | Kairis - partial payment (ATM shortfall from last week) | Kairis | 150 | cash | Yes | Paid | 2026-07-20
2026-06-24 | Materials | Kairis - remaining balance | Kairis | 45 | cash | Yes | Committed
2026-07-11 | Materials | Kairis - SikaGrout HP340 order (200 bags) + steel - partly delivered Sep; outstanding balance per Vicky Oct 3 EUR1,950 incl. EUR45 old balance (Sep 29 EUR4,400 -> EUR3,000 before Oct 3 payment; EUR400 gap vs logged payments, see flag 13) | Kairis | 1905 | cash | Yes | Committed
2026-07-21 | Materials | Kairis - partial payment toward column/beam debt | Kairis | 1000 | cash | Yes | Paid | 2026-07-21
2026-09-12 | Plumbing | Water connection fee (mains) + water meter purchase - one-off, now connected to mains supply | Accountant (POS transfer attempted Sep 12, declined - payment method to be resolved) | 400 | pending | No | Committed
2026-09-29 | Labour | Workers wages - week of Sep 21-27 (crew back on site Sep 24) | Site crew | 950 | cash | Yes | Paid | 2026-09-29
2026-09-29 | Materials | Reinforcement steel, column ties, 15x D16 6m connecting bars + nails | Supplier | 750 | cash | Yes | Paid | 2026-09-29
2026-09-29 | Fuel | Petrol for concrete mixer (column pour) | Site | 40 | cash | Yes | Paid | 2026-09-29
2026-09-26 | Electrical | Electricity provider - 50% advance to reactivate 1969 meter + relocate to lower entrance (incl. install permit + supply approval); Vicky paid Sep 26, covered by Sep 29 withdrawal | Electricity provider | 250 | cash | Yes | Paid | 2026-09-29
2026-09-26 | Electrical | Electricity provider - remaining 50% for meter reactivation/relocation (Vicky Oct 3: paying Oct 4 from Oct 3 withdrawal) | Electricity provider | 250 | cash | Yes | Paid | 2026-10-04
2026-09-23 | Electrical | Electricity bill (meter still in Anagnostou name) - Vicky to hand cash to Stathis Oct 2 | Anagnostou (Stathis) | 192 | cash | Yes | Committed
|  |  | PAID — total | 108161.47
|  |  | COMMITTED (approved, unpaid) | 15945
|  |  | PAID — from NBG (cash/transfer) | 106133.92
|  |  | PAID — outside NBG (Wise/card) | 2027.55

## Funding (NBG Deposits)
Funding — Deposits into NBG Account
Israel → NBG GR18 0110 3180 0000 3180 0400 611. All amounts EUR received. Source: bank transfer confirmations in /Money Transfers.
Value date | Amount (€) | Bank ref | Greek-side confirmation | Counted?
2025-09-28 | 25000 | 55423 | PDF OtherBankMatachTransfer_25_09 to GR18-0400611 | Yes
2025-09-28 | 15000 | 55758 | PDF OtherBankMatachTransfer_26_09 | Yes
2025-10-12 | 130000 | 63360 | PDF OtherBankMatachTransfer_12_10 | Yes
2026-01-11 | 10000 | 14452 | PDF OtherBankMatachTransfer_10_01 | Yes
2026-02-08 | 20000 | 30860 | Confirmed - bank statement (ref 30860) + project_data.js | Yes
2026-04-26 | 70000 | 70724 | PDF OtherBankMatachTransfer_26_04 | Yes
2026-05-31 | 2000 | 90833 | Transfer to WISE as backup - not spent; NOT a Greek NBG deposit | No
2026-07-13 | 50000 | wire-Jul13 | Kobi confirmed - Israel to NBG transfer (Mizrahi) | Yes
TOTAL DEPOSITS (counted) | 320000
Ground truth: Mizrahi-Tefahot euro account statement (Sikum Haavarot Matach 2.pdf, 01/01/2024-22/06/2026). Rows above are the transfer-to-another-bank lines to the Greek NBG account in the project period. 2024 transfers (EUR 10k, 1.7k) excluded as pre-project.
Israeli euro account still held ~EUR 64,786 liquid + EUR 70,000 in a term deposit (23-Apr) as of 10-Jun-2026 - available for future project funding.

## Property Acquisition 2025
Property Acquisition (2025)
Purchase of two-storey residence + plot, Agios Nikolaos. Contract price €145,000 (objective value €239,793.82). Paid from NBG account.
Date | Item | Payee | Amount (€) | From NBG? | Note
2025-09-29 | House payment 1 - pre-agreement advance | Anagnostou | 18500 | Yes | Bank transfer
2025-10-22 | House payment 2 - via Zoe (issued check to seller) | Anagnostou / Zoe | 107000 | Yes | Bank transfer to Zoe -> check to Anagnostou
2025-10-22 | House payment 2 - balance (direct) | Anagnostou | 19731 | Yes | Direct bank transfer
2025-10-17 | Purchase tax (FMA, incl 0.9% joint discount) | via Zoi Koliou | 7410 | Yes | Transfer to Zoe
2025-11-05 | Zoe commission | Zoi Koliou | 4350 | Yes | ATM cash via our debit card (800+2000+1000+550)
2025-11-05 | Attorney - Vasiliki | Vasiliki | 2000 | Yes | Cash withdrawn by Zoe
2025-11-05 | Land registration fee | Vasiliki | 1328 | Yes | Transfer to Vasiliki (pays on our behalf)
2025-10-24 | Notary (Vasiliki) | Mavri / Vasiliki | 2490 | Yes | Direct bank transfer
2025-09-29 | Legalization (engineer) - transfer 1 | Vicky (Revolut LT) | 800 | Yes | Pergola/rooftop/2 warehouses/wells
2025-10-01 | Legalization (engineer) - transfer 2 | Vicky (Revolut LT) | 520 | Yes
2025-10-01 | Legalization (engineer) - transfer 3 | Antonis | 680 | Yes
2025 | Legalization (engineer) - cash balance | Cash | 3000 | Yes | Cash portion (total legalization = EUR 5,000)
2025 | Notary & apostille - NBG account setup | - | 2700 | No | Paid from Israel (to open the account)
2025 | Flight to Evia - purchase trip | - | 1200 | No | Travel, paid from Israel
|  | ACQUISITION TOTAL (all) | 171709
|  | of which paid from NBG | 167809
Source: 'Agio Nikolaos house payments' sheet, 'Actual' table. House price EUR 145,231 (18,500 + 107,000 + 19,731).

## Out-of-NBG & Reimburse
Payments Outside NBG + Vicky Reimbursements
Project costs paid via Wise or by card (not from the NBG account), plus reimbursement transfers to Vicky. These expenses are already counted once in the Renovation Ledger.
Date | Item | Method | Amount (€) | Note
2026-06-06 | Bathroom fixtures (Diamantopoulos) | Wise | 614 | In ledger
2026-06-18 | Athens shopping - Yael unit fit-out | card (Vicky) | 972.55 | In ledger; reimbursed €972.55 below
2026-06-19 | Spanish tiles (Tsintonis) | Wise | 286 | In ledger; NBG was blocked
2026-06-22 | Bedding/pillows/bedspread - Yael | card (Vicky) | 155 | In ledger; to net vs window cost
|  | Subtotal | 2027.55
REIMBURSEMENTS TO VICKY (cash-flow only — not additional project cost)
Date | Item | Method | Amount (€) | Note
2026-06-22 | Reimburse Athens/Praktiker card spend | Wise → Revolut | 972.55 | Settles only the €972.55 Praktiker spend (not the €380 drill). LT853250002013391261

## Category Rollup
Category Rollup — Paid vs Budget
Paid = actuals from the Renovation Ledger (SUMIF). Budget = working estimates (Budget Overview / project_data forecast). Remaining is indicative.
Category | Paid to date (€) | Working budget (€) | Notes
Labour | 32650 | 25000 | Workers, Meli, ESAT, Ilir, contractors
Materials | 42357.87 | 25000 | Kairis main account, Amanatidis, sundries
Plumbing | 7119 | 9000 | All floors; ~€7.2k balance after water connection
Electrical | 2825 | 11250 | GF+storage approved €11,250; upper floors TBD
Site Works | 4300 | 6000 | Excavation, 160m road, compaction
Roof | 4225 | 4500 | 3F panels, storage roofs
Windows/Iron | 1550 | 18700 | Storage done; ~25 house openings upcoming
Waste/Bins | 2097 | 2000 | Recycle/waste containers
Tiles | 286 | 25500 | €286 paid; ~€25k order+install upcoming
Furniture | 905 | 1000 | Yael unit bed, mattress, bedding
Legal/Admin | 7666 | 11350 | Insurance, certificates, SIM, accountant
Landscaping | 300 | 5000 | Gardener, irrigation
Fuel | 360 | 500 | Site fuel
Equipment | 770.6 | 500 | Tools
Other | 750 | 300 | Misc
TOTAL | 108161.47 | 145600

## Reconciliation
NBG Account Reconciliation (official statement)
Account 31800400611, period 01/10/2025-25/06/2026. Ties to the cent. Source: NBG statement export25-06-2026.xlsx.
| Opening balance 01/10/2025 | 21066.81 | Embeds Sep-2025: +EUR25k +EUR15k transfers, -EUR18,500 down-payment, -fees
| + Deposits received (in period) | 230000 | EUR130k (13-Oct) + EUR10k (12-Jan) + EUR20k (09-Feb) + EUR70k (27-Apr)
| - Property acquisition & legal (transfers) | -139459.28 | House 126,730.81 + tax 7,410 + notary 2,490 + land reg 1,328.47 + owner cert 200 + land-reg temp 100 + legalization 620 + 580
| - Acquisition paid in cash (Nov-2025) | -6350 | Zoe commission 4,350 + Vasiliki 2,000
| - Renovation/project cash withdrawals (ATM) | -64730 | Cash for workers, Kairis, materials, etc.
| - Renovation card payments (POS) | -4494.92 | Amanatidis 1,524.32 + GKIZA 1,440 + aluminium 1,150 + drill 380.60
| - Accountant - tax registration | -711 | SIANOS PANTAZIS, 18-May
| - Personal card spend | -104.17 | Jan groceries/cafe (LIDL etc.)
| - Bank fees & charges | -14.5 | In-period commissions
| Computed closing balance | 35202.94
| Statement closing balance 25/06/2026 | 35202.94
| Difference (ties to zero) | 0
Cross-check - renovation funded from NBG
| Renovation from NBG per ledger | 106133.92
| Statement NBG renovation outflow (cash 64,730 + POS 4,494.92 + accountant 711) | 69935.92
| Difference = cash float / timing (+ ~300 legal items the statement groups under acquisition) | 36198
The NBG account is fully reconciled to the official statement - there is NO unexplained money.
The small ledger-vs-statement difference is cash float (cash withdrawn vs spent timing). ATM withdrawals are exact; renovation cash expenses are reconstructed weekly estimates.
ROLLING BRIDGE — since last full statement (2026-06-25)
| Opening — statement closing balance (2026-06-25) | 35202.94
| + Deposits since (dynamic — recalculates as new transfers are added) | 50000
| - Renovation paid from NBG since (dynamic — recalculates as new expenses are added) | 34610
| Computed balance (bridge) | 50592.94
| Reported balance (2026-10-05) | 49805
| Residual (bridge − reported) | 787.94
A residual here is expected cash-float/timing (ATM withdrawals vs itemized weekly reconstructions), or spending not yet reported to Kobi -- see Flags & Dedup. It is NOT unexplained/missing money unless it grows unexpectedly large or keeps widening.

## Flags & Dedup
Flags & De-duplication Log
Resolved items (green) and open questions (yellow). Nothing here is double-counted in the totals.
# | Issue | How handled | Status | Action needed
1 | Feb-8-2026 €20,000 transfer | Confirmed in the Mizrahi euro-account statement (ref 30860) and project_data.js. Counted in deposits. | Resolved | None.
2 | Hammer drill €380 (18-Jun) | Confirmed SEPARATE from the €972.55 Athens shopping; added as its own line, charged to the Antonis contract. | Resolved | Recover the €380 by deducting it from the Antonis contract balance.
3 | Vicky reimbursement €972.55 (Wise) | A settlement of the €972.55 Athens expense; shown only on the Out-of-NBG tab, never double-counted. | Resolved | None - you confirmed it was sent.
4 | May-28 cluster: excavator €600, plumber €1,000, electrician €1,000, plumber materials €300 | All FOUR confirmed real (WhatsApp 28-May + dashboard) and added to the ledger. | Resolved | None.
5 | Early items missing from Drive sheet: aluminium €1,150, plumber adv#1 €1,000, gate €50 | Confirmed they belong; added to the ledger. | Resolved | None.
6 | Acquisition detail and the €7,410 to Zoi | Itemised from the Actual table: €7,410 is the property purchase TAX (FMA); balance split €107,000 (Zoe check) + €19,731 direct. | Resolved | None.
10 | €2,000 transfer 31-May (ref 90833) | Went to Wise as an unspent backup buffer; excluded from NBG deposits. | Resolved | None.
7 | Reconciliation residual | RESOLVED with the official NBG statement: the account reconciles to the cent (€35,202.94). The earlier residual was an expenses-vs-deposits artifact, not missing money. | Resolved | None.
8 | Amanatidis + plumbing card payments (€2,140) | RESOLVED per Kobi: paid with the NBG debit card; reclassified as From NBG = Yes. | Resolved | None.
9 | Worker insurance Apr-Jun €3,858 | Not present in the NBG statement -> confirms still UNPAID. Listed as Committed. | OPEN | Pay/confirm; then it moves to Paid.
11 | EUR907.92 residual — rolling bridge (25-Jun to 11-Jul) | Kobi reported the current NBG balance as EUR23,505.02 on 11-Jul-2026. The ledger only accounts for EUR10,790 in NBG-paid cash-out since the 25-Jun statement (EUR35,202.94), projecting EUR24,412.94 -- EUR907.92 more than reported. Consistent with the known cash-float pattern (round ATM withdrawals vs itemized weekly reconstructions) but could also be spending Vicky hasn't reported yet. | OPEN | Ask Vicky to confirm — either an ATM withdrawal that ran ahead of itemized expenses, or a payment not yet reported in the WhatsApp group.
12 | Rolling bridge residual -EUR2,212.06 (Oct 2) | Anchor balance (EUR58,805) is from 29-Jul and predates the 25-Sep EUR3,000 withdrawal now logged as Paid (EUR2,350 Kairis + EUR650 unallocated float). Kobi said ~EUR58K on 24-Sep (approx, not used as anchor). Residual moved by exactly the EUR3,000 -- anchor staleness, not missing money. | Resolved | Superseded by flag 13 (fresh NBG balance EUR49,805 on Oct 5).
13 | NBG balance EUR49,805 (Oct 5) + Kairis EUR400 gap | Kobi reported EUR49,805 on 5-Oct = EUR58,805 (29-Jul) minus exactly three EUR3,000 ATM withdrawals (Sep 25, Sep 29, Oct 3). Sep 29 committed items (wages 950, steel 750, petrol 40, ELEC advance 250) + inferred Kairis 1,000 moved to Paid; Oct 3 report logged (wages 1,510, fuel 50, materials 150, ELEC 250, Kairis 1,050 = EUR3,010). Kairis: Sep 29 balance EUR4,400 minus logged EUR1,000 = EUR3,400, but Vicky Oct 3 says EUR3,000 -> EUR400 paid from somewhere unlogged (likely the Sep 25 EUR650 float). | OPEN | Ask Vicky: did EUR400 of the Sep 25 float go to Kairis? Confirm how the rest of the EUR650 float was spent. Rolling-bridge residual is the remaining cash-float timing gap.